{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["PMP Form (faux)"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"PMP Form (faux)","index":0,"n_rows":38,"n_cols":27,"rows_kept":38,"cut":false,"hidden":false,"merged":[[33,3,33,5],[33,9,33,25],[8,7,10,7],[8,8,10,8],[2,5,2,25],[2,2,2,3],[8,2,10,2],[8,3,10,3],[8,4,10,4],[8,5,10,5],[8,9,8,26],[9,9,10,9],[9,26,10,26],[4,3,5,3],[9,10,9,13],[9,14,9,17],[9,22,9,25],[9,18,9,21]]}
[]
[]
[null,null,"Project Information",null,null,"Performer Information"]
[null,null,"FOA Number:","DE-FOA-000XXXX",null,"Organization:",null,null,null,"Lead Institution",{"$nulls":5},"Institution 2",{"$nulls":6},"Institution 3"]
[null,null,"Project Title:","High Efficiency, Solution-Processable Organic Photovoltaics Based on Earth Abundant Charge-Recombination Interlayers",null,"Point of Contact:",null,null,null,"James Maxwell",{"$nulls":5},"Josef Stefan",{"$nulls":6},"Thomas Young"]
[{"$nulls":5},"E-mail Address:",null,null,null,"james.maxwell@e3devices.com",{"$nulls":5},"josef.stefan@inst2.com",{"$nulls":6},"thomas.young@inst3.com"]
[{"$nulls":5},"Phone Number:",null,null,null,"(555) 555-7743",{"$nulls":5},"(571) 222-2172",{"$nulls":6},"(112) 358-1321"]
[]
[null,null,"SOPO Item Identification Number","Item Description","Item Target Performance Metric","Item Performer ",null,"DOE Budget","Cost Share Budget","Planned"]
[{"$nulls":6},"Item Budget",null,null,"Start Date",2012,null,null,null,2013,null,null,null,2014,null,null,null,2015,null,null,null,"End Date"]
[{"$nulls":10},"Q1","Q2","Q3","Q4","Q1","Q2","Q3","Q4","Q1","Q2","Q3","Q4","Q1","Q2","Q3","Q4"]
[null,null,"T-1.1","Synthesis development of colloidal nanoparticles",null,"e3","$","$","$","2012-10-01",null,null,null,"X","X","X",{"$nulls":10},"2013-06-30"]
[null,null,"ST-1.1.1","Synthesize ~6 nm diameter iron oxide nanoparticles.","6nm diameter synthesis","e3","$","$","$","2012-10-01",null,null,null,"X","X","X",{"$nulls":10},"2013-06-30"]
[null,null,"ST-1.1.2","Develop synthesis of iron oxide nanoparticles of varying diameter (4, 6, 8, and 10 nm).","4,6,8,10 nm diameter synthesis","e3","$","$","$","2013-01-01",{"$nulls":4},"X","X",{"$nulls":10},"2013-06-30"]
[null,null,"M (T-1.1)","Development of four procedures for the syntheses of iron oxide nanoparticles of varying diameter (4, 6, 8, and 10 nm, +/- 1 nm). ","4 test-verified procedures","e3","N/A","N/A","N/A","N/A",{"$nulls":5},"X",{"$nulls":10},"2013-06-30"]
[null,null,"T-1.2","Interface energetics optimization of nanoparticle/organic interface",null,"e3; inst2","$","$","$","2013-07-01",{"$nulls":6},"X","X","X",{"$nulls":7},"2014-03-31"]
[null,null,"ST-1.2.1","Determine work function, ionization potential, and electron affinity of iron oxide nanoparticles of different sizes.","Characterization of nanoparticles","inst2","$","$","$","2013-07-01",{"$nulls":6},"X","X",{"$nulls":8},"2013-12-31"]
[" ",null,"ST-1.2.2","Develop a model for organic/nanoparticle/organic interface energetics.","Energetics model","inst2","$","$","$","2013-10-01",{"$nulls":7},"X","X",null," ",{"$nulls":5},"2014-03-31"]
[null,null,"M (T-1.2)","Selection of a nanoparticle system that allows for favorable device operation based upon the band-edge offset diagram generated from experimental data. ","Nanoparticle system downselection","e3; inst2","N/A","N/A","N/A","N/A",{"$nulls":8},"X",null," ",{"$nulls":5},"2014-03-31"]
[null,null,"G/NG-1","Identify the acceptor/iron oxide nanoparticle/donor system that will lead to the band-edge offset system for favorable device operation.","Energy map w/ ≥ 0.2eV delta","e3; inst2","N/A","N/A","N/A","N/A",{"$nulls":8},"X",{"$nulls":7},"2014-03-31"]
[null,null,"T-2.1","Lab-scale nanoparticle thin-film deposition protocol",null,"e3; inst3","$","$","$","2014-04-01",{"$nulls":9},"X","X","X","X",null,null,null,"2015-03-31"]
[null,null,"ST-2.1.1","Retrofit roll-to-roll (R2R) applicator with new liquid volume delivery systems and UV curing lamps.","Equipment upgrade","inst3","$","$","$","2014-04-01",{"$nulls":9},"X","X",{"$nulls":5},"2014-09-30"]
[null,null,"ST-2.1.2","Calibrate nanoparticle solution volume delivery.","Volume delivery calibration","inst3","$","$","$","2014-04-01",{"$nulls":9},"X","X",{"$nulls":5},"2014-09-30"]
[null,null,"M (ST-2.1.2)","Deposition of nanoparticle solution over a meter-wide flexible substrate to give a 10 nm thick film, +/- 2 nm.","Film thickness = 10nm","inst3","N/A",null,null,"2014-07-01",{"$nulls":10},"X",{"$nulls":5},"2014-09-30"]
[null,null,"ST-2.1.3","Measure a variety of nanoparticle thin-films via four-point probe measurements and optimize the system to obtain sheet resistance values of < 100 ohms/sq. ","Sheet resistance ≤ 100 ohms/sq.","e3; inst3","$","$","$","2014-10-01",{"$nulls":11},"X","X",null,null,null,"2015-03-31"]
[null,null,"M (T-2.1)","Demonstrate optimized film with both deposition of a 10 nm +/- 2 nm thin-film based on iron oxide nanoparticles of chosen size, and with a sheet resistance < 100 ohms/sq. over a substrate that is at least a meter wide.","Film thickness = 10nm, sheet resistance ≤ 100 ohms/sq.","e3; inst3","N/A","N/A","N/A","N/A",{"$nulls":12},"X",null,null,null,"2015-03-31"]
[null,null,"T-2.2","Lab-scale nanoparticle thin-film deposition optimization ",null,"e3; inst3","$","$","$","2015-01-01",{"$nulls":12},"X","X","X",null,"2015-09-30"]
[null,null,"ST-2.2.1","Fabricate R2R devices with 1.0 cm2 device area and at least 10% in-house certified device efficiencies.","Device efficiency ≥ 10%","e3; inst3","$","$","$","2015-01-01",{"$nulls":12},"X","X",null,null,"2015-06-30"]
[null,null,"ST-2.2.2","Fabricate R2R sub-modules with a device area of 225 cm2 and an efficiency of at least 6%, in-house certified.","Sub-module efficiency ≥ 6%","e3; inst3","$","$","$","2015-04-01",{"$nulls":13},"X",null,null,"2015-06-30"]
[null,null,"ST-2.2.3","Obtain device (1.0 cm2) and sub-module (225 cm2) National Renewable Energy Laboratory (NREL) certified efficiencies of at least 10% and 6%, respectively.","Device efficiency ≥ 10%, sub-module efficiency ≥ 6%","e3; inst3","$","$","$","2015-04-01",{"$nulls":13},"X","X",null,"2015-09-30"]
[null,null,"M (T-2.2)","A 1.0 cm2 device with an NREL certified efficiency of 10% under standard testing conditions (ASTM G173).","Device efficiency ≥ 10%","e3; inst3","N/A","N/A","N/A","N/A",{"$nulls":14},"X",null,"2015-09-30"]
[null,null,"FD-1","A tandem organic photovoltaic device (1.0 cm2) with an NREL certified efficiency of 10%.","Device efficiency ≥ 10%","e3; inst2; inst3","N/A","N/A","N/A","N/A",{"$nulls":14},"X",null,"2015-09-30"]
[null,null,"FD-2","A tandem organic photovoltaic sub-module (225 cm2) with an NREL certified efficiency of 6%.","Sub-module efficiency ≥ 6%","e3; inst2; inst3","N/A","N/A","N/A","N/A",{"$nulls":14},"X",null,"2015-09-30"]
[null,null,"SUM","N/A",null,null,"$     (Running SUM)","$    (Running SUM)","$     (Running SUM)","N/A",{"$nulls":16},"Date Summation Perormed"]
[]
[{"$nulls":12}," "]
[{"$nulls":5}," "]
[{"$nulls":4}," ",{"$nulls":11}," "]