{"text_format":"2","workbook":"xls","n_sheets":2,"sheets":["Tier 1 Template","Tier 2 Template"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Tier 1 Template","index":0,"n_rows":20,"n_cols":6,"rows_kept":20,"cut":false,"hidden":false,"merged":[[13,1,14,2],[13,3,14,3],[13,4,14,4],[13,5,14,5],[19,5,21,5],[18,1,18,2],[15,1,16,2],[15,3,16,3],[15,4,16,4],[15,5,16,5],[19,0,21,0],[19,1,21,2],[19,3,21,3],[19,4,21,4],[17,1,17,2],[7,1,8,2],[7,3,8,3],[7,4,8,4],[7,5,8,5],[11,4,12,4],[11,5,12,5],[9,1,10,2],[9,3,10,3],[9,4,10,4],[9,5,10,5],[11,1,12,2],[11,3,12,3],[3,0,3,5],[5,3,6,3],[5,4,6,4],[0,0,0,5],[1,0,1,5],[2,0,2,1],[2,2,2,3],[2,4,2,5],[4,1,4,2],[5,1,6,2],[5,5,6,5]],"flags":["formulas_cached_only"]}
["Tier 1: DELIVERABLE TABLE"]
["Incubator Company: "]
["PI: ",null,"Ph: ",null,"E-mail: "]
["12-Month Duration"]
["Task Number and Title","Criteria and Deliverable                                (Specific, Measurable, Achievable, Relevant, Timely) What, How, Who, Where?",null,"Date (Months after contract start)","% of total DOE funding*"," Additional Notes"]
["--",null,null,1,0.2,"Unencapsulated and packaged with desiccant.  Must be tested immediately after removal from packaging"]
[" Baseline Performance"]
[2,null,null,3,0.15,"Work with DOE to determine the best measurement technique to verify this uniformity over the full device area"]
["Process Integration"]
[1,null,null,5,0.1,"Same requirements as baseline deliverable"]
["Performance"]
[3,null,null,7,0.1,"Thermal cycling and light soaking done in accordance with IEC testing standards as permitted by DOE facilities"]
["Reliability Testing"]
[2,null,null,10,0.15]
["Process Integration"]
[1,null,null,12,0.3]
["Final  Prototype Deliverable"]
["**Quarterly Technical Progress Reports",null,null,null,"--","Short letter format, emphasizing status"]
["Draft/Final Technical Progress Report",null,null,null,"---"]
["Final Review",null,null,"12-months after subcontract execution",null,"Detailed accomplishments and status"]

{"sheet":"Tier 2 Template","index":1,"n_rows":34,"n_cols":6,"rows_kept":34,"cut":false,"hidden":false,"merged":[[33,3,34,3],[33,4,34,4],[29,1,30,2],[29,3,30,3],[29,4,30,4],[31,1,31,2],[33,5,34,5],[6,3,7,3],[6,4,7,4],[32,1,32,2],[29,5,30,5],[23,5,24,5],[14,5,15,5],[17,0,17,5],[14,1,15,2],[14,3,15,3],[14,4,15,4],[23,1,24,2],[23,3,24,3],[23,4,24,4],[33,0,34,0],[33,1,34,2],[18,4,19,4],[12,4,13,4],[12,5,13,5],[18,5,19,5],[16,1,16,2],[3,0,3,5],[4,1,4,2],[5,1,5,2],[6,1,7,2],[6,5,7,5],[0,0,0,5],[1,0,1,5],[2,0,2,1],[2,2,2,3],[2,4,2,5],[20,1,21,2],[20,3,21,3],[20,4,21,4],[20,5,21,5],[8,1,9,2],[8,3,9,3],[8,4,9,4],[8,5,9,5],[10,5,11,5],[12,1,13,2],[12,3,13,3],[10,1,11,2],[10,3,11,3],[10,4,11,4],[18,1,19,2],[18,3,19,3],[25,1,26,2],[25,3,26,3],[25,4,26,4],[25,5,26,5],[27,1,28,2],[27,3,28,3],[27,4,28,4],[27,5,28,5]],"flags":["formulas_cached_only"]}
["Tier 2: Deliverable Table"]
["Incubator Company: "]
["PI: ",null,"Ph: ",null,"E-mail: "]
["Phase I"]
["Baseline-to-Date"]
["Task Number and Title","Criteria and Deliverable                                (Specific, Measurable, Achievable, Relevant, Timely) What, How, Who, Where?",null,"Date (Months after contract start)","% of total DOE funding*"," Additional Notes"]
["--",null,null,2,0.1,"To be verified at DOE within experimental uncertainty"]
["Baseline Performance"]
[2,null,null,4,0.05,"We will work with DOE to determine the best measurement technique to verify this uniformity over the full device area."]
["Process Integration"]
[1,null,null,5,0.1,"To be verified at DOE within experimental uncertainty"]
["Cell Performance"]
[3,null,null,7,0.05,"Thermal cycling and light soaking done in accordance with IEC testing standards as permitted by DOE facilities"]
["Preliminary Reliability Testing"]
[2,null,null,8,0.05,"We will work with DOE to determine the best measurement technique to verify this uniformity over the full device area."]
["Process Integration"]
["9-Month Mark",null,null,9,0.1,"Demonstrate adequate pilot production"]
["Phase II"]
[1,null,null,11,0.05,"Verification of online program"]
["Advanced Cell Performance"]
[3,null,null,13,0.05,"Demonstrates interconnect forces sufficient for module assembly"]
["Reliability Testing"]
["Reliability Testing"]
[4,null,null,14,0.05,"Costs based on equipment quotes and name plate capacity substantiated by current throughput"]
["Cost Performance"]
[4,null,null,15,0.05,"Costs based on equipment quotes and name plate capacity substantiated by current throughput"]
["Cost Performance"]
[3,null,null,16,0.05,"Demonstrates interconnect forces sufficient for module assembly"]
["Reliability Testing"]
[5,null,null,18,0.3,"Demonstration of a pilot-production run-rate (cells/h) and how this corresponds to a yearly run-rate (kW)"]
["Scale-up"]
["**Quarterly Technical Progress Report",{"$nulls":4},"Short letter format, emphasizing status"]
["Draft/Final Technical Progress Reports"]
["Final Review"]