{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["PMP Form (faux)"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"PMP Form (faux)","index":0,"n_rows":41,"n_cols":23,"rows_kept":41,"cut":false,"hidden":false,"merged":[[5,2,6,2],[0,0,1,22],[11,6,11,9],[11,10,11,13],[11,18,11,21],[11,14,11,17],[10,0,12,0],[10,1,12,1],[10,2,12,2],[10,3,12,3],[10,4,12,4],[10,5,10,22],[11,5,12,5],[11,22,12,22],[3,4,3,21],[3,1,3,2]]}
["Project Management Plan (PMP)"]
[]
[]
[null,"Project Information",null,null,"Performer Information"]
[null,"FOA Number:","DE-FOA-000XXXX",null,"Number:",1,{"$nulls":5},2,{"$nulls":6},3]
[null,"Project Title:","High Efficiency, Photovoltaic Model System",null,"Organization:","Lead Institution",{"$nulls":5},"Institution 2",{"$nulls":6},"Institution 3"]
[{"$nulls":4},"Point of Contact:","James Maxwell",{"$nulls":5},"Josef Stefan",{"$nulls":6},"Thomas Young"]
[{"$nulls":4},"E-mail Address:","james.maxwell@e3devices.com",{"$nulls":5},"josef.stefan@inst2.com",{"$nulls":6},"thomas.young@inst3.com"]
[{"$nulls":4},"Phone Number:","(555) 555-7743",{"$nulls":5},"(571) 222-2172",{"$nulls":6},"(112) 358-1321"]
[]
["Budget Period","SOPO Item Identification Number","Item Description","Tool(s) and/or Method(s) of Measurement","Item Performer ","Planned"]
[{"$nulls":5},"Start Date",2013,null,null,null,2014,null,null,null,2015,null,null,null,2016,null,null,null,"End Date"]
[{"$nulls":6},"Q1","Q2","Q3","Q4","Q1","Q2","Q3","Q4","Q1","Q2","Q3","Q4","Q1","Q2","Q3","Q4"]
[1,"T-1","Comprehensive Model System Design",null,1,"2013-10-01",null,null,null,"X","X","X",{"$nulls":10},"2014-06-30"]
[1,"ST-1.1","Identification of necessary doping density, defect density and stoichiometry of absorber",null,1,"2013-10-01",null,null,null,"X","X","X",{"$nulls":10},"2014-06-30"]
[1,"ST-1.2","Identification of capable emitter materials to compliment the chosen absorber construction (doping density, defect density, resistivity, surface passivation, depositon/growth technique, etc.)",null,1,"2013-10-01",null,null,null,"X","X","X",{"$nulls":10},"2014-06-30"]
[1,"ST-1.3","Identification of absorber synthesis pathways/techniques and cell construction ",null,1,"2014-01-01",{"$nulls":4},"X","X",{"$nulls":10},"2014-06-30"]
[1,"M (T-1)","Completion of ab-initio calculations and alpha computer modeling of material systems","Report, Software Output",1,"N/A",{"$nulls":4},"X",{"$nulls":11},"2014-03-30"]
[1,"M (T-1)/ Go/No-Go","Comprehensive report  of model system design with identification of cell characterizatics (doping density, defect density, interfaces, etc.) and synthesis pathway","Report",1,"N/A",{"$nulls":6},"X",{"$nulls":9},"2014-09-30"]
["1, 2","T-2","Cell Modeling",null,"1 & 2","2014-01-01",{"$nulls":4},"X","X","X","X","X",{"$nulls":7},"2015-03-31"]
["1, 2","ST-2.1","Data entry and simulation for absorber characteristics. Itterations done to identify key performance characterisics (doping density, defect density, carrier lifetime, stoichiometry, etc.)","Software (Version)",2,"2014-04-01",{"$nulls":5},"X","X","X",{"$nulls":8},"2014-12-31"]
["1, 2","ST-2.2","Develop a model for absorber and emitter interface","Software (Version)",2,"2014-07-01",{"$nulls":6},"X","X",null,null," ",{"$nulls":5},"2014-12-31"]
["1, 2","ST-2.2=3","Develop a full cell model ","Software (Version)",2,"2014-10-01",{"$nulls":7},"X","X",null," ",{"$nulls":5},"2015-03-31"]
["1, 2","M (T-2)","Identification of absorber which will have highest performance","Report, Software Output","1 & 2","N/A",{"$nulls":7},"X",null,null," ",{"$nulls":5},"2014-12-31"]
["1, 2","M (T-2)","Identification of cell architecture which will have highest performance","Report, Software Output","1 & 2","N/A",{"$nulls":8},"X",{"$nulls":7},"2015-03-31"]
["2, 3","T-3","Material Growth and Characterization",null,"1 & 3","2015-04-01",{"$nulls":9},"X","X","X","X",null,null,null,"2016-03-31"]
[2,"ST-3.1","Retrofit tooling for deposition/growth technique specifications needed for absorber material development","CVD Retrofit",3,"2015-04-01",{"$nulls":9},"X","X",{"$nulls":5},"2015-09-30"]
[2,"ST-3.2","Initial absorber growth- Doping density (XXXX), Defect Density (XXXX), carrier lifetime (XXXX), stoichiometry,etc.","CVD, SCM, XRD, SE, HRTEM, SIMS",3,"2015-04-01",{"$nulls":9},"X","X",{"$nulls":5},"2015-09-30"]
[2,"M (ST-3.2)/ Go/No-Go","Grow/deposit absorber with carrier lifetimes >XXXX, doping density of XXXX, defect density of XXXX. Verified by NREL","Material Characterized at NREL",3,"2015-07-01",{"$nulls":10},"X",{"$nulls":5},"2015-09-30"]
[3,"ST-3.3","Characterization of Interface made with absorber and emmitter of choice ","SCM, XRD, SE, HRTEM, SIMS","1 & 3","2015-10-01",{"$nulls":11},"X","X",null,null,null,"2016-03-31"]
[3,"M (ST-3.3)","Demonstrate optimized absorber XXmicron +/- X microns (Carrier lifetime XXXX, Doping Density XXXX, Defect Density XXXX, etc.) and optimized emitter  XXmicron +/- X microns (sheet resistance XXXX, etc.)","Material Characterized at NREL","1 & 3","N/A",{"$nulls":12},"X",null,null,null,"2016-03-31"]
["2, 3","T-4","Model System Cell Synthesis and Characterization",null,"1 & 3","2015-04-01",{"$nulls":9},"X","X","X","X","X","X",null,"2016-09-30"]
[2,"ST-4.1","Fabricate devices with 1.0 cm2 device area and at least 10% in-house certified device efficiencies.","CVD, CB, Screen Print Contact, I-V Characterization","1 & 3","2015-04-01",{"$nulls":9},"X",{"$nulls":6},"2015-06-30"]
[2,"ST-4.2","Fabricatedevices with a device area of 1.0 cm2 and an efficiency of at least 15%, in-house certified.","CVD, CB, Screen Print Contact, I-V Characterization","1 & 3","2015-07-01",{"$nulls":10},"X",{"$nulls":5},"2015-09-30"]
[3,"M (T-4)","A  photovoltaic cell (~1 cm2) with an NREL certified efficiency = World Record % for material system. (ASTM G173).","Device Characterization at NREL","1 & 3","N/A",{"$nulls":11},"X",{"$nulls":4},"2015-12-31"]
[3,"ST-4.3","Fabricate 1.0 cm2 cell > world record efficiency for material system","CVD, CB, Screen Print Contact, I-V Characterization","1 & 3","2016-04-01",{"$nulls":12},"X","X","X",null,"2016-09-30"]
[3,"FM-1","A  photovoltaic cell (~1 cm2) with an NREL certified efficiency of >29% (ASTM G173).","Device Characterization at NREL","1, 2 & 3","N/A",{"$nulls":14},"X",null,"2016-09-30"]
["X","T-5, 6, 7….","Additional Tasks- It is expected that more than 4 work tasks will be required to complete these projects. Please repeat format of above tasks until all work tasks for the proposed project have been thoroughly covered.","Examples: TRPL, SIMS, XRD, SEM, TEM, Simulation Software Version X, Report, Device, etc.","1, 2 & 3","N/A"]
[{"$nulls":8}," "]
[{"$nulls":4}," "]
[null,null,null," ",{"$nulls":8}," "]